## Sheet1
Risk ID | Risk Description | Impact | Likelihood | Response Plan | Owner
R1 | API downtime during peak hours | High | Medium | Add monitoring and fallback endpoint | DevOps
R2 | User data leak through insecure endpoints | Critical | Low | Use HTTPS, OAuth, and token encryption | Security Lead
R3 | UI design delay from external team | Medium | High | Add buffer time in Gantt, daily follow-ups | PM
R4 | Vendor contract failure for hosting | High | Medium | Short-term backup vendor, penalty clause | Legal