## Sheet1
Task | Assigned To | Estimated Time (hrs) | Hourly Rate ($) | Estimated Cost ($)
UI Design | Fatima | 6 | 15 | 90
Frontend Implementation | Sara | 10 | 18 | 180
Backend API Development | Ali | 12 | 20 | 240
Database Setup | Ali | 5 | 20 | 100
Testing & QA | Ayesha | 8 | 18 | 144
Project Management | Fahad | 4 | 25 | 100
|  | 45 |  | 854